## Sheet1
Test # | Setup | Trigger | Verification | Pass Condition | Fail Condition | Status | Weight | Comments
1 | User Registration | User is in the main page | Application loads the user registration form | All required fields completed | Missing required fields | complete | 10%
2 | Create Pet Profile | User is in the Pet Profiles Page | The application loads the new pet profile form | All required fields completed | Missing required fields | complete | 20%
3 | Add Module | User is in the Modules Page | The application loads the new module form | All required fields completed | Missing required fields | complete | 30%
4 | Edit Module | User is in the Modules page and selects desired module | The application allows the user to open the module details form with values preloaded | All required fields completed | Missing required fields | In process | 5% | There is an error in the web configuration that does not allows me to render data from the JSON
5 | Remove Module | User is editing the module | Application ask for module removal confirmation | Deletion success | No module found | In process | 5% | There is an error in the web configuration that does not allows me to render data from the JSON
6 | Edit Pet Profile | User is in the pet profiles page and selects desired profile | Application loads the pet profile form with the values preloaded | All required fields completed | Missing required fields | In process | 5% | There is an error in the web configuration that does not allows me to render data from the JSON
7 | Login | User is in the main page | User needs to be authenticated. | All required fields completed | Missing required fields | In process | 10% | There is an error in the web configuration that does not allows me to render data from the JSON
8 | Edit User Account | User is in the user settings page | Application allows the user to change the user account settings. | All required fields completed | Missing required fields | In process | 5% | There is an error in the web configuration that does not allows me to render data from the JSON
9 | Remove User Account | User is in the user settings page | Application asks for removal confirmation | Deletion success | No account found | In process | 5% | There is an error in the web configuration that does not allows me to render data from the JSON
[6 empty] | Total | 100%